## Gantt Chart Data
Task | Start Date | Duration (days) | End Date
Assemble Project Group | 2026-08-24 | 3 | 2026-08-26
Select Project | 2026-08-27 | 12 | 2026-09-07
Determine Project Constraints | 2026-09-08 | 14 | 2026-09-21
Create Project B.O.M. | 2026-09-22 | 4 | 2026-09-25
Design Project Circuit Board | 2026-09-28 | 26 | 2026-10-23
Assemble Project Circuit Board | 2026-10-26 | 12 | 2026-11-06
Complete Embedded Systems Programming | 2026-10-26 | 19 | 2026-11-13
Test and Verify Power Delivery | 2026-11-16 | 5 | 2026-11-20
Test and Verify I/O Functions | 2026-11-23 | 5 | 2026-11-27
Complete Mobile Application Programming | 2026-11-30 | 54 | 2027-01-22
Test and Verify Wireless Communication | 2027-01-25 | 5 | 2027-01-29
Design Circuit Enclosure | 2027-02-01 | 12 | 2027-02-12
Assemble Final Circuit Enclosure | 2027-02-15 | 12 | 2027-02-26
Present Project to Faculty | 2027-05-06 | 1 | 2027-05-06